## Лист1
Epic | Priority | Short Name | Done | Details | Area | Time (estimated) hours
Planning | Must | 1. Analysis |  | Create project vision, time estimation etc | Planning | 2
Planning | Must | 2. Planing Architecture of Application |  |  | Analysing | 3
WEB UI | Must | 3. UI |  | Flexible user interface
WEB UI | Must | 3.1 Nav template |  | One vision of navigation part (top) | WebUI/Front End | 2
WEB UI | Must | 3.2 Footer template |  | Footer template for each page | WebUI/Front End | 1
WEB UI | Must | 3.1 Welcome page |  | General info, advertisements, hot deals etc | WebUI/Front End | 5
WEB UI | Must | 3.2 Registration page |  | Register using e-mail or social network accounts | WebUI/Front End | 3
WEB UI | Must | 3.3 Login page |  | Login using e-mail or social network accounts | WebUI/Front End | 1
WEB UI | Must | 3.4 Profile page |  | Quick access and change profile information | WebUI/Front End | 10
WEB UI | Must | 3.5. Work pages
WEB UI | Must | 3.5.1. Admin - goods page |  | Page for editing DB respect to goods | WebUI/Front End | 5
WEB UI | Must | 3.5.2. Admin - users page |  | Page for editing user accounts (block,delete etc) | WebUI/Front End | 2
WEB UI | Must | 3.5.2. Admin - orders page |  | Preview current orders | WebUI/Front End | 4
WEB UI | Must | 3.5.3. Change photo view |  | Pop up window with photo editing abilities | WebUI/Front End | 3
WEB UI | Must | 3.5.1. Goods preview page |  | Page for preview all goods | WebUI/Front End | 5
WEB UI | Must | 3.5.2. Detail info page |  | Page with detail information about some good | WebUI/Front End | 5
WEB UI | Must | 3.5.3. Cart preview page |  | Preview cart and editing it | WebUI/Front End | 3
WEB UI | Must | 3.5.3. Error page |  | For showing details about occured error | WebUI/Front End | 2
Features | Must | 4. Features
Features | Must | 4.1 Work with goods (admin)
Features | Must | 4.1.1 Edit categories/subcategories |  | Editing - add,delete,rename categories, groups. Change image for them | Back End | 4
Features | Must | 4.1.1 Edit brand and features |  | Add new brand, edit old one. | Back End | 4
Features | Must | 4.1.1 Edit description |  | Change, create description for good | Back End | 5
Features | Must | 4.1.1 Uploading photos |  | Upload new background photo and illustrations for each good. MAX quantity - 5 | Back End | 8
Features | Must | 4.1.1 Change available quantity for good |  | Manage quantity in warehouse | Back End | 1
Features | Should | 4.1.1 Lock user |  |  | Back End | 1
Features | Must | 4.2 User
Features | Must | 4.6 Registartion |  | User registration | Back End | 4
Features | Must | 4.7 Authorization |  | User authorization | Back End | 2
Features | Must | 4.1.1 Submit order |  | Manage quantity in warehouse |  | 5
Features | Must | 4.1.1 Edit and preview cart |  | Manage quantity in warehouse |  | 10
Features | Should | 4.9 Change avatar |  | Change user avatar | Back End | 5
Features | Should | 4.9 Get notification and check on email |  | Send notification on user' email | Back End | 4
Developing | Must | 5. Database |  | Database which includes all information | Back End
Developing | Must | 5.1 Database diagram |  | Create ER-diagram | Back End | 10
Developing | Must | 5.2 Transactions |  | Create transactions | Back End | 1
Developing | Must | 11. Cl server |  | Deployment project in internet | Back End
Start | 2016-06-27 | Document is not full
Sprint count | 4
Today | 2016-08-03
Time (estimated) hours | 120